## Sheet1
Issue # | Task Summary | Est Time (Mins) | Coding Effort (Mins) | Non-Coding Effort (Mins) | Estimator | Implementor
M1
1.01 | Landing Page Dev | 20 | 22 | 5 | Ahnasia | Ahnasia
1.02 | Sign In Page Dev | 30 | 45 | 40 | Ahnasia | Ahnasia
1.03 | PP Dev | 45 | 30 | 30 | Jaimes | Jaimes
1.04 | Courses Dev | 75 | 120 | 45 | Jaimes | Jaimes
1.05 | DB info | 60 | 90 | 45 | Zack | Zack
1.06 | Deploy to Vercel | 40 | 40 | 10 | Zack | Zack
M2
2.01 | User Auth | 15 | 40 | 30 | Jaimes | Jaimes
2.02 | User Auth Check | 20 | 20 | 15 | Jaimes | Jaimes
2.03 | Seed DB with SRCH content | 90 | 50 | 45 | Zack | Jaimes + Zack
2.04 | Admin Functions | 70 | 45 | 30 | Ahnasia | Ahnasia
2.041 | Fix Sign Up Page | 15 | 20 | 43 | Ahnasia | Ahnasia
2.05 | Unmapped Forum | 90 | 90 | 45 | Ahnasia | Ahnasia
2.06 | Mapping Adjustments | 60 | 45 | 15 | Jaimes | Jaimes
2.07 | Refactor SRCH integration | 30 | 20 | 20 | Jaimes | Jaimes
2.08 | Modify seed.ts | 60 | 60 | 10 | Jaimes | Jaimes
2.09 | Enable + Update Search bar | 30 | 20 | 0 | Jaimes | Jaimes
2.1 | Improve Browser/Course Readability | 40 | 45 | 45 | Jaimes | Jaimes
2.11 | Curriculum Page Dev | 90 | 120 | 30 | Jaimes | Jaimes
M3
3.01 | Implement course CRUD for courses | 50 | 60 | 15 | Ahnasia | Ahnasia
3.02 | Adjust page styles and design | 70 | 80 |  | Zack | Zack
3.03 | Edit Note readability | 20 | 30 | 10 | Jaimes | Jaimes
3.04 | Complete Seed.ts | 30 | 60 | 60 | Zack | Zack
3.05 | Update Curriculum | 30 | 30 | 30 | Jaimes | Jaimes
3.06 | Update Profile Options | 25 | 30 | 5 | Zack | Zack
3.07 | Add Objectives Update | 20 | 20 | 10 | Jaimes | Jaimes
3.08 | Instructor forum expansion | 35 | 63 | 10 | Ahnasia | Ahnasia

## Sheet2
Team Member | SD Experience | How was Coding Effort Tracked? | How was Non-Coding Effort Tracked?
Ahnasia Goulbourne | 6 Months | Tracked Github Commits | Best Guess/ Tracking clock time
Jaimes Mexia-Santiago | 11 Months | Manual Timer / Timestamps on GitHub Push / Estimate | Best Guess / Using dedicated time slots from manual scheduling
Zackary Lown | 4 years | Manual Timer / Timestamps on GitHub Push / Estimate | Estimated right after